## project_planning
Feature | Taks | Estimations (hours) | Effort (hours) | Effort (hours) | status | Comment
Design structure | Research to find libraries suporting with flask framework to build MVC web application | 3 | 4 | 4 hours | Done
| Read the documentation of SQLAlchemy | 2 | 2 | 2 hours | Done
Implement Auth | Read the documentation of flask_login | 4 | 4 | 4 hours | Done
| Read documentation of WTForms | 2 | 2 | 2 hours | Done
| User email verification | 4 |  |  | Pending | Deprioratised
| User Registration with testing | 4 | 4 | 8 hours | Done
| user Login | 1 | 1 |  | Done
| Update password | 1 | 1 | 2 hours | Done
| Update profile | 1 | 1 | 2 hours | Done
| Front end validation | 3 |  |  | Pending | Deprioratised
Design the template | Check for a design (desided to follow the design of https://realfood.tesco.com/) | 4 | 4 | 8 hours | Done
| Create template | 6 | 6 | 8 hours | Done
| Integrade the templage with flask project | 2 | 2 | 2 hours | Done
Extend the Models | Create Models for recipe, recipe categories to generate data base | 6 | 6 | 6 hours | Done
| Created the seed.py file to load initial data | 2 | 2 | 2 hours | Done
| Integrate the home page with flask application data | 2 | 2 |  | Done
Create Pages of main nav | Home page style changes and log design | 3 | 3 |  | Done
| Category listign pages | 2 | 2 |  | Done
Recipe create/edite/delete | Recipe create page | 6 | 6 |  | Done
| Recipe edite page | 4 | 4 |  | Pending
| Recipe delte | 3 | 3 |  | Pending
Deployment | Deploy project in vps | 2 | 2 |  | Done
About page and documentation | Readme on git | 2 | 2 |  | Done
| About page | 4 | 4 |  | Done
Testing on vps | I have tested the features in each state of the product in locan and vps | 6 | 6 |  | Done

## test
Issue | Fix | State | Comments
The additional methods and ingredients are missing when user submit the recipe create form with errors. | The issue will not be visible to user after adding ront-end validation | pending | known issue
Alignment issues | Not to be fixed | done | ignored as this is a sample project